## Project schedule
| ABC BOOKSTORE CHATBOT |  |  |  |  | Project start: | [7 empty] | 2024-12-13
[6 empty] | Display week: | [7 empty] | 1
[6 empty] | 2024-12-09 | [6 empty] | 2024-12-16 | [6 empty] | 2024-12-23 | [6 empty] | 2024-12-30 | [6 empty] | 2025-01-06 | [6 empty] | 2025-01-13 | [6 empty] | 2025-01-20 | [6 empty] | 2025-01-27 | [6 empty] | 2025-02-03 | [6 empty] | 2025-02-10 | [6 empty] | 2025-02-17 | [6 empty] | 2025-02-24 | [6 empty] | 2025-03-03 | [6 empty] | 2025-03-10 | [6 empty] | 2025-03-17 | [6 empty] | 2025-03-24 | [6 empty] | 2025-03-31 | [6 empty] | 2025-04-07 | [6 empty] | 2025-04-14 | [6 empty] | 2025-04-21 | [6 empty] | 2025-04-28 | [6 empty] | 2025-05-05 | [6 empty] | 2025-05-12 | [6 empty] | 2025-05-19 | [6 empty] | 2025-05-26 | [6 empty] | 2025-06-02
| TASK | START | END | DAYS | time axis 2024-12-09 to 2025-06-08
 | time axis 2024-12-09 to 2025-06-08
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Project Initiation and Planning
| Gather and document detailed requirements from ABC Book Store | 2024-12-13 | 2024-12-18 |  | 6
| Develop a comprehensive project plan | 2024-12-19 | 2024-12-24 |  | 6
| Design the chatbot's architecture | 2024-12-25 | 2025-01-04 |  | 11
Development and Implementation
| Develop and test the chatbot's core functionalities | 2025-01-05 | 2025-01-15 |  | 11
| Implement natural language processing (NLP) capabilities | 2025-01-16 | 2025-01-31 |  | 16
| Populate the chatbot's knowledge base with relevant information | 2025-02-01 | 2025-02-11 |  | 11
Testing and Refinement
| Conduct thorough user testing of the chatbot | 2025-02-12 | 2025-02-17 |  | 6
| Analyze user feedback and refine the chatbot | 2025-02-18 | 2025-02-23 |  | 6
| Ensure the chatbot meets all the requirements of ABC Book Store | 2025-02-24 | 2025-03-06 |  | 11
Deployment and Launch
| Deploy the chatbot on the ABC Book Store website | 2025-03-07 | 2025-03-12 |  | 6
| Announce the launch of the chatbot to ABC Book Store's customers | 2025-03-13 | 2025-03-14 |  | 2
| Monitor the chatbot's performance and gather initial user feedback | 2025-03-15 | 2025-03-29 |  | 15
Post-Launch Monitoring and Optimization
| Continuously monitor the chatbot's performance | 2025-03-30 | 2025-04-09 |  | 11
| Identify areas for optimization and implement updates | 2025-04-10 | 2025-04-15 |  | 6
| Provide support and maintenance for the chatbot until ABC Book Store takes ownership | 2025-04-16 | 2025-04-26 |  | 11